CRIT MODULE 06

PILOT IMPLEMENTATION PLAN (DRAFT)

Climate-Resilient School Infrastructure Toolkit

1. PILOT OBJECTIVE

To field-test CRIT tools and demonstrate cost-effective, scalable retrofitting solutions that reduce climate-related disruptions and improve safety of school infrastructure.

2. PILOT COVERAGE

Recommended pilot scale:

- 10–20 schools in 2–3 climate-vulnerable districts

- Mix of flood-prone and heat-exposed sites

3. DISTRICT SELECTION CRITERIA

- high hazard exposure (flood/heat/storm)

- high poverty and vulnerability index

- history of school closures/damage

- weak infrastructure conditions

- low availability of alternative schools nearby

4. IMPLEMENTATION PHASES

Phase 1: Preparation (Weeks 1–4)

- stakeholder onboarding and approvals

- training of district engineers and planners

- baseline data collection

Phase 2: School Assessment (Weeks 5–8)

- apply CRIT risk screening tool

- develop retrofit packages per school

- prepare BOQs and budgets

Phase 3: Retrofitting Implementation (Weeks 9–18)

- procurement and contracting

- construction works with safety compliance

- community engagement and monitoring

Phase 4: Post-Implementation Review (Weeks 19–24)

- endline assessment

- cost-benefit analysis

- documentation of results and lessons learned

5. GOVERNANCE STRUCTURE

- Provincial Steering Committee (policy guidance)

- District Implementation Unit (execution)

- School Management Committee (community ownership)

- Technical Support Team (quality assurance)

6. OUTPUTS

- schools assessed using CRIT tools

- schools retrofitted with resilience upgrades

- trained engineers and planners

- toolkit refined based on field learning

7. KEY OUTCOME INDICATORS

- reduction in school closure days

- improved safety compliance scores

- improved thermal comfort indicators

- reduced flood damage incidents

- increased community engagement in maintenance