PROJECT TITLE:

Climate-Resilient School Infrastructure Toolkit (CRIT)

IMPLEMENTING PARTNER:

WUM Advisory Services

ALIGNMENT:

UNICEF Safe Schools Initiative | Climate Resilience | Education in Emergencies (EiE)

------------------------------------------------------------

1. OVERALL GOAL (IMPACT LEVEL)

------------------------------------------------------------

Strengthen climate resilience of public school infrastructure in Pakistan to ensure safe, uninterrupted, and equitable learning for children in hazard-prone communities.

INDICATORS:

- Reduction in climate-related school closure days

- Reduction in school infrastructure damage from floods, heatwaves, and storms

- Increased proportion of schools meeting minimum safety standards

MEANS OF VERIFICATION:

- Education department attendance records

- School infrastructure assessments

- Disaster impact reports (PDMA/NDMA)

- CRIT monitoring data

------------------------------------------------------------

2. OUTCOME LEVEL

------------------------------------------------------------

Outcome 1:

Improved resilience and safety of public school infrastructure in climate-vulnerable districts.

INDICATORS:

- % improvement in composite school safety scores (CRIT index)

- % reduction in infrastructure vulnerability scores

- Number of schools upgraded to “Safe/Moderate Risk” category

Outcome 2:

Improved continuity of learning during climate shocks.

INDICATORS:

- Reduction in annual school closure days

- % increase in student attendance during monsoon/heatwave periods

- Reduced learning material loss due to disasters

Outcome 3:

Strengthened institutional capacity for climate-resilient education infrastructure planning.

INDICATORS:

- Number of district engineers trained in CRIT tools

- Number of schools assessed using standardized toolkit

- Integration of CRIT tools into district planning systems

------------------------------------------------------------

3. OUTPUT LEVELS

------------------------------------------------------------

Output 1: Schools assessed and prioritized using CRIT tools

INDICATORS:

- Number of schools assessed using risk screening tool

- Number of schools ranked by composite risk score

- % of schools mapped with hazard exposure data

Output 2: Climate-resilient retrofitting implemented

INDICATORS:

- Number of schools retrofitted using CRIT packages

- Number of flood/heat/storm resilience upgrades completed

- % of schools meeting minimum safety compliance standards

Output 3: Capacity building conducted

INDICATORS:

- Number of engineers, planners, and teachers trained

- % improvement in pre/post training assessment scores

- Number of training sessions delivered

Output 4: Monitoring and evaluation system operational

INDICATORS:

- Functional M&E dashboard established

- Baseline and endline assessments completed

- Regular reporting cycles implemented

------------------------------------------------------------

4. ACTIVITIES

------------------------------------------------------------

Activity 1:

Conduct climate risk screening and vulnerability assessment of schools

Activity 2:

Develop school prioritization lists based on composite risk scoring

Activity 3:

Design and implement modular retrofitting packages:

- Flood protection systems

- Heat mitigation systems

- Storm resilience upgrades

- WASH infrastructure upgrades

- Accessibility and inclusion improvements

Activity 4:

Develop and implement training programs for district staff and contractors

Activity 5:

Establish monitoring, evaluation, and reporting systems

Activity 6:

Conduct community engagement and School Management Committee training

------------------------------------------------------------

5. KEY ASSUMPTIONS

------------------------------------------------------------

- Government cooperation at provincial and district levels

- Availability of basic construction materials and contractors

- Community willingness to participate in school maintenance

- Stable funding for pilot implementation phase

- No extreme climate shocks exceeding design thresholds during implementation

------------------------------------------------------------

6. RISKS AND MITIGATION MEASURES

------------------------------------------------------------

Risk 1: Delayed procurement and implementation

Mitigation: Pre-approved vendor lists and simplified procurement mechanisms

Risk 2: Poor construction quality

Mitigation: Technical supervision and quality assurance checklists

Risk 3: Limited community engagement

Mitigation: School Management Committee integration and awareness campaigns

Risk 4: Budget constraints

Mitigation: Modular phased implementation approach

Risk 5: Extreme climate events during implementation

Mitigation: Adaptive implementation scheduling and emergency protocols

------------------------------------------------------------

7. SUSTAINABILITY STRATEGY

------------------------------------------------------------

- Integration into government education planning systems

- Capacity building of local engineers and district staff

- Community ownership through School Management Committees

- Use of low-cost, locally sourced materials

- Preventive maintenance planning embedded in school operations

- Open-source toolkit for national replication

------------------------------------------------------------

8. SCALABILITY STRATEGY

------------------------------------------------------------

CRIT is designed as a scalable model through:

- Standardized assessment tools

- Modular retrofit packages

- Simple scoring and prioritization system

- Low-cost implementation framework

- Adaptability across provinces and climate zones

------------------------------------------------------------